## Extranet
Steps | Sub function | Screen | Expected date | Note
Create layout and functions for admin | for admin | Dashboard | 2019-09-03
| for agency/promoter | Dashboard | 2019-09-03
| for staff | Dashboard | 2019-09-03
Function add advertisement to frontend |  |  | 2019-09-05 | Funtion validate user will be implemented while we do frontend
Layout and logic funtion for Account | create/edit for admin | Account | 2019-09-11
| create/edit for agency/promoter | Account | 2019-09-11
| edit for staff | Account | 2019-09-11
Layout and logic function of Property |  | Property | 27/09/2019
Layout and logic function of Property Match |  | Property Match | 2019-09-01
Layout and function for Vender |  | Vender | 2019-10-05
Statistic function |  | Statis | 2019-10-08
Complete Extranet website |  |  | 2019-10-12

## Portal
Steps | Expected date | Note
Layout for all .basic interface (not fully designed) | 22/10/2019
Advertisement content from extranet | 25/10/2019
Function search agency and select compatible agency(Modal1 ,2) | 28/10/2019
Action create document ( Modal 3) | 2019-11-01
Regrate design and content for website | 2019-11-04
User register | 2019-11-08
Function validate new user from Extranet | 2019-11-09 | in Extranet website
Fix related problem | 15/11/2019